## Executive Summary
Metric | Value
Compliance Percentage | 42.2
Maturity Score | 1.39
Total Controls | 41
Controls With Gaps | 37
Critical Gaps | 12
High Priority Items | 19
Total Implementation Cost | 1088000
Annual Maintenance Cost | 215000
Total Risk Reduction | 2928000
Program Roi | 169.1
Payback Period Months | 4.5
Maturity Vs Industry | -1.41
Compliance Vs Industry | -32.8
Average Evidence Score | 3
Total Annual Exposure | 6680000
Residual Risk After Implementation | 3752000

## Gap Analysis
Control_ID | Control_Name | Category | Subcategory | Criticality | Business_Impact | Current_Maturity | Target_Maturity | Gap | Evidence_Score | Implementation_Cost | Annual_Maintenance | Effort_Days | Implementation_Complexity | Business_Criticality | Regulatory_Pressure | Risk_Reduction_Value | ROI_Score | Priority_Score | Department | NIST_Mapping | Dependencies | Next_Review | Implementation_Priority
A.5.1 | Information security policies | Organizational | Policies | Critical | Legal | 2 | 4 | 2 | 3 | 15000 | 3000 | 30 | Low | 5 | 2 | 0 | 0 | 10.6 | IT Security | ID.GV-1 |  | 2026-07-01
A.6.1 | Information security roles and responsibilities | Organizational | Structure | High | Operational | 1 | 3 | 2 | 3 | 8000 | 2000 | 20 | Low | 3 | 1 | 0 | 0 | 7.4 | HR | ID.GV-2 | A.5.1 | 2026-07-01 | Critical
A.6.2 | Segregation of duties | Organizational | Controls | High | Financial | 0 | 3 | 3 | 3 | 12000 | 1500 | 25 | Low | 4 | 1 | 0 | 0 | 10.1 | Internal Audit | PR.AC-4 | A.6.1 | 2026-07-01
A.6.3 | Contact with authorities | Organizational | External Relations | Medium | Legal | 1 | 2 | 1 | 3 | 3000 | 500 | 10 | Low | 3 | 2 | 0 | 0 | 6.7 | Legal | RS.CO-4 |  | 2026-07-01 | Critical
A.6.4 | Contact with special interest groups | Organizational | External Relations | Low | Reputational | 1 | 2 | 1 | 3 | 2000 | 400 | 8 | Low | 1 | 0 | 0 | 0 | 2.7 | Communications | RS.CO-5 |  | 2026-07-01 | Medium
A.6.5 | Information security in project management | Organizational | Project Management | High | Operational | 0 | 3 | 3 | 3 | 10000 | 2500 | 35 | Low | 3 | 0 | 0 | 0 | 8.1 | PMO | ID.SC-1 | A.5.1, A.14.1 | 2026-07-01 | Critical
A.6.6 | Information security agreements | Organizational | Agreements | Medium | Legal | 2 | 3 | 1 | 3 | 5000 | 1000 | 15 | Low | 3 | 1 | 0 | 0 | 5.9 | Legal | ID.SC-2 | A.5.1 | 2026-07-01 | High
A.6.7 | Remote work | Organizational | Remote Work | High | Operational | 2 | 4 | 2 | 3 | 25000 | 5000 | 45 | Low | 3 | 0 | 0 | 0 | 6.6 | IT Operations | PR.AC-1 | A.9.1, A.13.1 | 2026-07-01 | Critical
A.6.8 | Information security event reporting | Organizational | Incident Management | Critical | Operational | 1 | 4 | 3 | 3 | 20000 | 4000 | 40 | Low | 4 | 2 | 0 | 0 | 10.9 | SOC | DE.AE-1 | A.16.1 | 2026-07-01
A.7.1 | Screening | People | Pre-employment | Medium | Reputational | 2 | 3 | 1 | 3 | 8000 | 1200 | 20 | Low | 2 | 1 | 34000 | 4.25 | 6.7 | HR | PR.IP-11 |  | 2026-07-01 | Critical
A.7.2 | Terms and conditions of employment | People | Employment | High | Legal | 3 | 3 | 0 | 3 | 2000 | 300 | 8 | Low | 4 | 1 | 0 | 0 | 5.6 | HR | PR.IP-11 | A.7.1 | 2026-07-01 | High
A.7.3 | Disciplinary process | People | Employment | Medium | Legal | 1 | 2 | 1 | 3 | 4000 | 800 | 12 | Low | 3 | 0 | 0 | 0 | 5.1 | HR | PR.IP-11 | A.7.2 | 2026-07-01 | High
A.7.4 | Information security awareness, education and training | People | Training | High | Operational | 1 | 4 | 3 | 3 | 35000 | 8000 | 60 | Low | 3 | 2 | 375000 | 10.71 | 11.7 | IT Security | PR.AT-1 | A.5.1 | 2026-07-01
A.7.5 | Termination or change of employment | People | Termination | High | Operational | 2 | 3 | 1 | 3 | 6000 | 1000 | 15 | Low | 3 | 1 | 0 | 0 | 5.9 | HR | PR.IP-12 | A.9.2 | 2026-07-01 | High
A.7.6 | Confidentiality or non-disclosure agreements | People | Legal | High | Legal | 3 | 3 | 0 | 3 | 3000 | 500 | 10 | Low | 4 | 1 | 0 | 0 | 5.6 | Legal | PR.IP-11 |  | 2026-07-01 | High
A.8.1 | Inventory of information and other associated assets | Technology | Asset Management | Critical | Operational | 1 | 4 | 3 | 3 | 45000 | 8000 | 80 | Medium | 4 | 1 | 0 | 0 | 10.1 | IT Operations | ID.AM-1 |  | 2026-07-01
A.8.2 | Information classification | Technology | Classification | High | Legal | 0 | 3 | 3 | 3 | 25000 | 4000 | 50 | Low | 4 | 1 | 270000 | 10.8 | 12.1 | Data Governance | ID.AM-5 | A.8.1 | 2026-07-01
A.8.3 | Information handling | Technology | Information Handling | High | Legal | 1 | 3 | 2 | 3 | 20000 | 3000 | 40 | Low | 4 | 1 | 0 | 0 | 8.6 | All Departments | PR.DS-5 | A.8.2 | 2026-07-01 | Critical
A.9.1 | Access control policy | Technology | Access Control | Critical | Operational | 2 | 4 | 2 | 3 | 18000 | 3500 | 35 | Low | 4 | 1 | 0 | 0 | 8.6 | IT Security | PR.AC-1 | A.5.1 | 2026-07-01 | Critical
A.9.2 | Access to networks and network services | Technology | Network Access | Critical | Operational | 2 | 4 | 2 | 3 | 40000 | 8000 | 70 | Medium | 4 | 0 | 0 | 0 | 7.8 | Network Team | PR.AC-3 | A.9.1, A.13.1 | 2026-07-01 | Critical
A.9.3 | User access management | Technology | User Management | Critical | Operational | 3 | 4 | 1 | 3 | 30000 | 6000 | 50 | Low | 4 | 1 | 124000 | 4.13 | 9.1 | Identity Management | PR.AC-1 | A.9.1 | 2026-07-01 | Critical
A.9.4 | System and application access control | Technology | System Access | Critical | Operational | 2 | 4 | 2 | 3 | 35000 | 7000 | 60 | Low | 4 | 0 | 248000 | 7.09 | 9.8 | Application Security | PR.AC-4 | A.9.3 | 2026-07-01 | Critical
A.10.1 | Cryptographic controls | Technology | Cryptography | High | Legal | 0 | 3 | 3 | 3 | 50000 | 10000 | 90 | Medium | 4 | 1 | 0 | 0 | 10.1 | IT Security | PR.DS-1 | A.5.1 | 2026-07-01
A.11.1 | Physical security perimeters | Physical | Perimeter Security | High | Operational | 2 | 3 | 1 | 3 | 25000 | 4000 | 30 | Low | 3 | 0 | 37500 | 1.5 | 6.6 | Physical Security | PR.AC-2 |  | 2026-07-01 | Critical
A.11.2 | Physical entry | Physical | Access Control | High | Operational | 3 | 3 | 0 | 3 | 15000 | 2000 | 20 | Low | 3 | 0 | 0 | 0 | 3.6 | Physical Security | PR.AC-2 | A.11.1 | 2026-07-01 | Medium
A.12.1 | Operational procedures and responsibilities | Operational | Operations | Medium | Operational | 2 | 3 | 1 | 3 | 12000 | 2000 | 25 | Low | 2 | 0 | 0 | 0 | 3.9 | IT Operations | PR.IP-1 |  | 2026-07-01 | Medium
A.12.2 | Change management | Operational | Change Management | High | Operational | 1 | 4 | 3 | 3 | 35000 | 6000 | 65 | Medium | 3 | 0 | 0 | 0 | 8.1 | Change Management | PR.IP-3 | A.12.1 | 2026-07-01 | Critical
A.12.3 | Information backup | Operational | Backup | Critical | Operational | 2 | 4 | 2 | 3 | 40000 | 8000 | 50 | Low | 4 | 0 | 250000 | 6.25 | 9.8 | IT Operations | PR.IP-4 |  | 2026-07-01 | Critical
A.12.4 | Event logging | Operational | Logging | Critical | Legal | 1 | 4 | 3 | 3 | 60000 | 12000 | 100 | High | 5 | 2 | 477000 | 7.95 | 14.1 | SOC | DE.AE-3 |  | 2026-07-01
A.12.5 | Clock synchronization | Operational | Time Management | Medium | Operational | 3 | 3 | 0 | 3 | 5000 | 800 | 10 | Low | 2 | 0 | 0 | 0 | 2.4 | IT Operations | DE.AE-1 |  | 2026-07-01 | Medium
A.13.1 | Network controls | Technology | Network Security | High | Operational | 2 | 3 | 1 | 3 | 45000 | 9000 | 75 | Medium | 3 | 0 | 0 | 0 | 5.1 | Network Security | PR.AC-5 |  | 2026-07-01 | High
A.13.2 | Information transfer | Technology | Data Transfer | High | Legal | 1 | 3 | 2 | 3 | 30000 | 5000 | 55 | Low | 4 | 1 | 0 | 0 | 8.6 | IT Security | PR.DS-2 | A.13.1 | 2026-07-01 | Critical
A.14.1 | Information security requirements analysis and specification | Technology | SDLC | High | Operational | 0 | 3 | 3 | 3 | 25000 | 5000 | 60 | Low | 3 | 0 | 0 | 0 | 8.1 | Application Security | ID.SC-1 | A.5.1 | 2026-07-01 | Critical
A.14.2 | Secure development life cycle | Technology | SDLC | High | Operational | 0 | 3 | 3 | 3 | 40000 | 8000 | 80 | Medium | 3 | 0 | 142500 | 3.56 | 10.1 | Development | ID.SC-1 | A.14.1 | 2026-07-01
A.15.1 | Information security policy for supplier relationships | Organizational | Supplier Management | High | Operational | 1 | 3 | 2 | 3 | 15000 | 3000 | 35 | Low | 3 | 1 | 95000 | 6.33 | 9.4 | Procurement | ID.SC-2 | A.5.1 | 2026-07-01 | Critical
A.15.2 | Addressing security within supplier agreements | Organizational | Supplier Management | Medium | Legal | 1 | 3 | 2 | 3 | 10000 | 2000 | 25 | Low | 3 | 1 | 95000 | 9.5 | 9.4 | Legal | ID.SC-3 | A.15.1 | 2026-07-01 | Critical
A.16.1 | Management of information security incidents and improvements | Operational | Incident Management | Critical | Operational | 1 | 4 | 3 | 3 | 75000 | 15000 | 120 | High | 4 | 2 | 375000 | 5 | 12.9 | SOC | RS.RP-1 | A.6.8, A.12.4 | 2026-07-01
A.17.1 | Planning information security continuity | Operational | Business Continuity | Critical | Operational | 0 | 4 | 4 | 3 | 85000 | 17000 | 140 | High | 4 | 1 | 150000 | 1.76 | 13.36 | Business Continuity | RC.RP-1 | A.12.3 | 2026-07-01
A.17.2 | Information processing facilities redundancy | Technology | Redundancy | High | Operational | 1 | 3 | 2 | 3 | 120000 | 24000 | 90 | High | 3 | 0 | 75000 | 0.62 | 7.22 | Infrastructure | RC.CO-1 | A.17.1 | 2026-07-01 | Critical
A.18.1 | Compliance with legal and contractual requirements | Organizational | Compliance | Critical | Legal | 2 | 4 | 2 | 3 | 30000 | 6000 | 70 | Medium | 5 | 2 | 180000 | 6 | 12.6 | Compliance | ID.GV-3 | A.5.1 | 2026-07-01
A.18.2 | Information security reviews | Organizational | Reviews | High | Operational | 1 | 3 | 2 | 3 | 25000 | 5000 | 40 | Low | 3 | 0 | 0 | 0 | 6.6 | Internal Audit | ID.GV-4 |  | 2026-07-01 | Critical

## Implementation Roadmap
Control_ID | Control_Name | Implementation_Priority | Priority_Score | Implementation_Phase | Estimated_Start | Estimated_End | Implementation_Cost | Effort_Days | ROI_Score | Department | Dependencies | Dependency_Risk | Business_Impact
A.12.4 | Event logging |  | 14.1 | Phase 1 | 2025-07-01 | 2025-09-29 | 60000 | 100 | 7.95 | SOC |  | Medium | Legal
A.17.1 | Planning information security continuity |  | 13.36 | Phase 1 | 2025-07-01 | 2025-09-29 | 85000 | 140 | 1.76 | Business Continuity | A.12.3 | Medium | Operational
A.16.1 | Management of information security incidents and improvements |  | 12.9 | Phase 1 | 2025-07-01 | 2025-09-29 | 75000 | 120 | 5 | SOC | A.6.8, A.12.4 | Medium | Operational
A.18.1 | Compliance with legal and contractual requirements |  | 12.6 | Phase 2 | 2025-09-29 | 2025-12-28 | 30000 | 70 | 6 | Compliance | A.5.1 | Medium | Legal
A.8.2 | Information classification |  | 12.1 | Phase 2 | 2025-09-29 | 2025-12-28 | 25000 | 50 | 10.8 | Data Governance | A.8.1 | Medium | Legal
A.7.4 | Information security awareness, education and training |  | 11.7 | Phase 2 | 2025-09-29 | 2025-12-28 | 35000 | 60 | 10.71 | IT Security | A.5.1 | Medium | Operational
A.6.8 | Information security event reporting |  | 10.9 | Phase 2 | 2025-09-29 | 2025-12-28 | 20000 | 40 | 0 | SOC | A.16.1 | Medium | Operational
A.5.1 | Information security policies |  | 10.6 | Phase 2 | 2025-09-29 | 2025-12-28 | 15000 | 30 | 0 | IT Security |  | Medium | Legal
A.6.2 | Segregation of duties |  | 10.1 | Phase 2 | 2025-09-29 | 2025-12-28 | 12000 | 25 | 0 | Internal Audit | A.6.1 | Medium | Financial
A.14.2 | Secure development life cycle |  | 10.1 | Phase 2 | 2025-09-29 | 2025-12-28 | 40000 | 80 | 3.56 | Development | A.14.1 | Medium | Operational
A.8.1 | Inventory of information and other associated assets |  | 10.1 | Phase 3 | 2025-12-28 | 2026-03-28 | 45000 | 80 | 0 | IT Operations |  | Medium | Operational
A.10.1 | Cryptographic controls |  | 10.1 | Phase 3 | 2025-12-28 | 2026-03-28 | 50000 | 90 | 0 | IT Security | A.5.1 | Medium | Legal
A.9.4 | System and application access control | Critical | 9.8 | Phase 3 | 2025-12-28 | 2026-03-28 | 35000 | 60 | 7.09 | Application Security | A.9.3 | Medium | Operational
A.12.3 | Information backup | Critical | 9.8 | Phase 3 | 2025-12-28 | 2026-03-28 | 40000 | 50 | 6.25 | IT Operations |  | Medium | Operational
A.15.2 | Addressing security within supplier agreements | Critical | 9.4 | Phase 3 | 2025-12-28 | 2026-03-28 | 10000 | 25 | 9.5 | Legal | A.15.1 | Medium | Legal
A.15.1 | Information security policy for supplier relationships | Critical | 9.4 | Phase 3 | 2025-12-28 | 2026-03-28 | 15000 | 35 | 6.33 | Procurement | A.5.1 | Medium | Operational
A.9.3 | User access management | Critical | 9.1 | Phase 4 | 2026-03-28 | 2026-06-26 | 30000 | 50 | 4.13 | Identity Management | A.9.1 | Medium | Operational
A.13.2 | Information transfer | Critical | 8.6 | Phase 4 | 2026-03-28 | 2026-06-26 | 30000 | 55 | 0 | IT Security | A.13.1 | Medium | Legal
A.9.1 | Access control policy | Critical | 8.6 | Phase 4 | 2026-03-28 | 2026-06-26 | 18000 | 35 | 0 | IT Security | A.5.1 | Medium | Operational
A.8.3 | Information handling | Critical | 8.6 | Phase 4 | 2026-03-28 | 2026-06-26 | 20000 | 40 | 0 | All Departments | A.8.2 | Medium | Legal
A.12.2 | Change management | Critical | 8.1 | Phase 4 | 2026-03-28 | 2026-06-26 | 35000 | 65 | 0 | Change Management | A.12.1 | Medium | Operational
A.6.5 | Information security in project management | Critical | 8.1 | Phase 4 | 2026-03-28 | 2026-06-26 | 10000 | 35 | 0 | PMO | A.5.1, A.14.1 | Medium | Operational
A.14.1 | Information security requirements analysis and specification | Critical | 8.1 | Phase 4 | 2026-03-28 | 2026-06-26 | 25000 | 60 | 0 | Application Security | A.5.1 | Medium | Operational
A.9.2 | Access to networks and network services | Critical | 7.8 | Phase 5 | 2026-06-26 | 2026-09-24 | 40000 | 70 | 0 | Network Team | A.9.1, A.13.1 | Medium | Operational
A.6.1 | Information security roles and responsibilities | Critical | 7.4 | Phase 5 | 2026-06-26 | 2026-09-24 | 8000 | 20 | 0 | HR | A.5.1 | Medium | Operational
A.17.2 | Information processing facilities redundancy | Critical | 7.22 | Phase 5 | 2026-06-26 | 2026-09-24 | 120000 | 90 | 0.62 | Infrastructure | A.17.1 | Medium | Operational
A.7.1 | Screening | Critical | 6.7 | Phase 5 | 2026-06-26 | 2026-09-24 | 8000 | 20 | 4.25 | HR |  | Medium | Reputational
A.6.3 | Contact with authorities | Critical | 6.7 | Phase 5 | 2026-06-26 | 2026-09-24 | 3000 | 10 | 0 | Legal |  | Medium | Legal
A.6.7 | Remote work | Critical | 6.6 | Phase 5 | 2026-06-26 | 2026-09-24 | 25000 | 45 | 0 | IT Operations | A.9.1, A.13.1 | Medium | Operational
A.11.1 | Physical security perimeters | Critical | 6.6 | Phase 5 | 2026-06-26 | 2026-09-24 | 25000 | 30 | 1.5 | Physical Security |  | Medium | Operational
A.18.2 | Information security reviews | Critical | 6.6 | Phase 5 | 2026-06-26 | 2026-09-24 | 25000 | 40 | 0 | Internal Audit |  | Medium | Operational
A.7.5 | Termination or change of employment | High | 5.9 | Phase 5 | 2026-06-26 | 2026-09-24 | 6000 | 15 | 0 | HR | A.9.2 | Medium | Operational
A.6.6 | Information security agreements | High | 5.9 | Phase 5 | 2026-06-26 | 2026-09-24 | 5000 | 15 | 0 | Legal | A.5.1 | Medium | Legal
A.7.3 | Disciplinary process | High | 5.1 | Phase 6 | 2026-09-24 | 2026-12-23 | 4000 | 12 | 0 | HR | A.7.2 | Medium | Legal
A.13.1 | Network controls | High | 5.1 | Phase 6 | 2026-09-24 | 2026-12-23 | 45000 | 75 | 0 | Network Security |  | Medium | Operational
A.12.1 | Operational procedures and responsibilities | Medium | 3.9 | Phase 6 | 2026-09-24 | 2026-12-23 | 12000 | 25 | 0 | IT Operations |  | Medium | Operational
A.6.4 | Contact with special interest groups | Medium | 2.7 | Phase 6 | 2026-09-24 | 2026-12-23 | 2000 | 8 | 0 | Communications |  | Medium | Reputational

## Regulatory Compliance
Regulation | Total_Controls | Controls_with_Gaps | Compliance_Score | Implementation_Cost | High_Priority_Controls | Status
GDPR | 6 | 6 | 39.1 | 235000 | 1 | Non-Compliant
NIS2 | 5 | 5 | 25 | 270000 | 0 | Non-Compliant
SOX | 4 | 4 | 33.3 | 137000 | 2 | Non-Compliant
PCI-DSS | 5 | 5 | 44.4 | 203000 | 2 | Non-Compliant

## Risk Scenarios
Risk_ID | Risk_Name | Threat_Actor | Likelihood | Impact | Inherent_Risk | Annual_Loss_Expectancy | Key_Controls
RISK-001 | Ransomware Attack | Cybercriminal Group | 4 | 5 | 20 | 2500000 | A.12.4, A.12.3, A.16.1
RISK-002 | Data Breach - Customer PII | Insider Threat | 3 | 5 | 15 | 1800000 | A.9.3, A.9.4, A.8.2
RISK-003 | Supply Chain Compromise | Nation State | 2 | 4 | 8 | 950000 | A.15.1, A.15.2, A.14.2
RISK-004 | Business Disruption | Natural Disaster | 2 | 4 | 8 | 750000 | A.17.1, A.17.2, A.11.1
RISK-005 | Privileged Account Abuse | Malicious Insider | 3 | 4 | 12 | 680000 | A.9.3, A.9.4, A.12.4

## Department Analysis
Department | Total_Gaps | Total_Cost | Total_Effort | Avg_Priority | Controls_Count
All Departments | 2 | 20000 | 40 | 8.6 | 1
Application Security | 5 | 60000 | 120 | 8.95 | 2
Business Continuity | 4 | 85000 | 140 | 13.36 | 1
Change Management | 3 | 35000 | 65 | 8.1 | 1
Communications | 1 | 2000 | 8 | 2.7 | 1
Compliance | 2 | 30000 | 70 | 12.6 | 1
Data Governance | 3 | 25000 | 50 | 12.1 | 1
Development | 3 | 40000 | 80 | 10.1 | 1
HR | 5 | 28000 | 75 | 6.14 | 5
IT Operations | 8 | 127000 | 210 | 6.56 | 5
IT Security | 12 | 148000 | 270 | 9.92 | 5
Identity Management | 1 | 30000 | 50 | 9.1 | 1
Infrastructure | 2 | 120000 | 90 | 7.22 | 1
Internal Audit | 5 | 37000 | 65 | 8.35 | 2
Legal | 4 | 21000 | 60 | 6.9 | 4
Network Security | 1 | 45000 | 75 | 5.1 | 1
Network Team | 2 | 40000 | 70 | 7.8 | 1
PMO | 3 | 10000 | 35 | 8.1 | 1
Physical Security | 1 | 40000 | 50 | 5.1 | 2
Procurement | 2 | 15000 | 35 | 9.4 | 1
SOC | 9 | 155000 | 260 | 12.63 | 3